- Identify the critical path and project total duration. Identify the slack available for each task. Discuss what would happen to the critical path if task E ends up lasting 19 days instead of the 12 estimated.

2

C = 6

4

F = 2

7

I = 6

10

A = 1

J = 5

M = 8

1

D = 7

5

G = 11

O = 2

8

K = 7

12

13

B = 3

3

H = 3

L = 4

N = 3

E = 12

6

9

11