## Info
Project Workbook Information
The project workbook allows project managers, team members, sponsors, and stakeholders to easily track and monitor project activities. Any of these worksheets can easily be broken out into separate documents.
Suggested Sheets for All Projects
Project Selection | Payback Method / Net Present Value / Project selection matrix

## Data
Project
Project #
Project manager
Sponsor
Project artifacts
Last updated

## Payback Method
Example
| Project A | Project B | Formulas
Investment | 700000 | 400000 | Project A Payback | (D5/D6)
Annual Savings | 225000 | 110000 | Project B Payback | (F5/F6)
Payback Period | 3.1111 | 3.6364
|  |  | Project A Rate of Return | (D6/D5)
Rate of Return | 32.14% | 27.5% | Project B Rate of Return | (F6/F5)
Accept Project A: Less than 5 years on return and Rate is greater than desired 15%
Accept Project B: Less than 5 years on return and Rate is greater than desired 15%
Payback Method | Project A | Project B |  |  | Payback Method | Project A | Project B
Investment | 1000000 | 425000 |  |  | Investment | 1250000 | 750000
Annual Savings | 200000 | 75000 |  |  | Annual Savings | 75000 | 125000
Payback Period = | 5 | 5.6667 |  |  | Payback Period = | 16.6667 | 6
Rate of Return = | 20% | 17.65% |  |  | Rate of Return = | 6% | 16.67%
Accept or Reject Project A? Less than 5 years on return and rate is greater than 15 |  |  |  |  | Accept or Reject Project A? More than 5 years on return period and the rate of return is less than 15
Accept or Reject Project B? More than 5 years on return and rate is greater than 15 |  |  |  |  | Accept or Reject Project B? More than 5 Years on payback period and the return is more than 15

## Net Present Value
Project A |  | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |  | Example
Required | 15%
Outflows |  | -700000 | [5 empty] | -700000
Inflows |  |  | 225000 | 225000 | 225000 | 225000 | 225000
Net Inflows |  |  | 225000 | 225000 | 225000 | 225000 | 225000 | 1125000 | Project A =E5+NPV(D4,F7:J7)
[8 empty] | 425000 | 54234.8971
Project B
Required | 15%
Outflows |  | -400000 | [5 empty] | -400000
Inflows |  |  | 110000 | 110000 | 110000 | 110000 | 110000 | 550000
Net Inflows |  |  | 110000 | 110000 | 110000 | 110000 | 110000 |  | Project B =E11+NPV(D10,F13:J13)
[8 empty] | 150000 | -31262.9392
Accept or Reject Project A and B
Project A |  | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Required | 15%
Outflows |  | -450000 | -100000
Inflows |  |  | 250000 | 300000 | 200000 | 200000 | 200000
Net Inflows |  |  | 150000 | 300000 | 200000 | 200000 | 200000 | 1050000 | 252567.1255
600000
Project B
Required | 15%
Outflows |  | -750000 |  | -100000
Inflows |  |  | 150000 | 150000 | 150000 | 150000 | 150000 | 750000
Net Inflows |  |  | 150000 | 50000 | 150000 | 150000 | 150000 |  | -322791.102
650000
Accept or Reject Projects A and B
Project A |  | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Required | 12%
Outflows |  | -600000 | -100000 | -50000 | -20000
Inflows |  |  | 300000 | 275000 | 275000 | 195000 | 205000 | 1250000
Net Inflows |  |  | 200000 | 225000 | 255000 | 195000 | 205000 |  | 179692.5449
1730000
Project B
Required | 12%
Outflows |  | -500000 |  | -100000 | -75000 | -50000
Inflows |  |  | 250000 | 200000 | 200000 | 250000 | 275000
Net Inflows |  |  | 250000 | 100000 | 125000 | 200000 | 275000 | 950000 | 175052.2054
Accept or Reject Projects A and B

## Project Selection Matrix
Page 56 | Film Prioritization Case
| Must Objectives |  | Must meet if impacts | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Meets all safety & environ. Stds |  | Y | y | y | n | y | y | y | y
N
N/A
| PG or G |  | Y | y | y | y | y | y | y | y
N
N/A
| No adverse effect on other operations |  | Y | y | n | n | n | y | y | n
N
N/A
| Want Objectives | Relative Imptc | Single project impact
| Win Best Pic | 70 | 0=No potential | 70 | 70 | 0 | 140 | 70 | 0 | 70
1=Low potential
2=high potential
| Win best animated feature | 60 | 0=No potential | 120 | 120 | 0 | 120 | 60 | 60 | 120
1=Low potential
2=high potential
| Gen addt'l merch | 10 | 0=No potential | 20 | 10 | 10 | 20 | 10 | 10 | 20
1=Low potential
2=high potential
| Raise environ concerns | 55 | 0=No potential | 0 | 0 | 110 | 110 | 0 | 55 | 110
1=Low potential
2=high potential
| Gen profit greater than 18% | 70 | 0=No potential | 140 | 140 | 70 | 70 | 70 | 70 | 140
1=Low potential
2=high potential
| Adv state of film animation | 40 | 0=No potential | 40 | 80 | 40 | 40 | 40 | 40 | 80
1=Low potential
2=high potential
| Provide basis for new theme ride | 10 | 0=No potential | 10 | 20 | 10 | 20 | 10 | 10 | 10
1=Low potential
2=high potential
|  |  | Total Weighted Score | 400 | 440 | 240 | 520 | 260 | 245 | 550
Priority
|  |  | Project # | 1 | 2 | 3 | 4 | 5 | 6 | 7

## WBS
Work Breakdown Structure
Project | [5 empty] | Project # | A car trip through several countries
Project manager | [5 empty] | Sponsor
Project artifacts | [5 empty] | Updated
ID | Task | Dependencies | Status - % Complete | Effort Hours | Cost | Start Date | Planned Completion | Actual Completion
1 | Initiate | ID # of task
2 |  | 1 Choese a relaiable car |  | 10 | 500 | 2017-02-10 | 2017-02-13
3 |  | 1.1 price estimates |  | 5 | 0 | 2017-02-14 | 2017-02-15
4 |  | 1.2 Decide how many people |  | 24 | 0 | 2017-02-16 | 2017-02-20
5 | Planning | Choese countries close to each other |  | 48 |  | 2017-02-27
6 |  | learn the maps |  | 48 | 300 | 2017-03-06 | 2017-03-10
7 |  | divide the days staying in each country |  | 24 | 300 | 2017-03-10 | 2017-03-13
8 | Execution | Travel to Eroup |  | 24 |  | 2017-03-15 | 2017-04-01
9 |  | Rent a great car for good price
10
11 | Control | try to stay on the plan
12 |  | make sure the car works fine from time to time
13
14 | Closeout | Make sure it was fun for my friends
15 |  | make sure eveything went as planed
Note on D6: Options are: Open Closed

## Basis of Estimate
Basis of Estimate
Project: | [5 empty] | Date:
Category | Material | Labor | Indirect Costs | Base Cost | Reserve | Total Cost | Funding Source | Cost Methodology
The project is about a car trip around several countries in the world. The projecrt will therefore invvolve all the costs tthat will be incurred during the trip. | Car hire: $ 100 fuel: $ 200 Food: $ 200 | Driver: $ 400 car maitainance: $ 80 carwash: $ 45 | possible puncture: $ 60 | Total cost: $ 1085 | Tour guide`s compaensation: $ 100 traffic compliance fee: $ 50 | Total sum: $ 1235 | The road trip is intended to gie a better picture of what the tour company should consider. This means that the sources of funds is from the ministyr o tourism and other tour agencies. | the cost estimates were derived from the budget by other agencies that have done the same or a similar researh which gave us a clear picture of what budget to expect.
WBS Description: A road trip requires things that surround the vehilce and the people on board. According to the cost estimates, every party has been considered to ensure the trip is eefective. The maintainace cost is expected to be low since the model of the vejhilce used is well maitained and strong. There is the need to consider the drivers and the tour guides who will be accompanying us through the journey. The cost of food has included those of the guides and the researchers who will be on the road for the period. The cost of fuel will be determined by the miles covered which have been budgeted according to other triips in the same region.
Cost Description: Being a road trip, the parties t hat will be involved and the attributes to consider are what will affect the facilities and the people. The records that other companies that havve conducted the trips is what we used in our budget estimation. This was important since it gaev us a clear record of what we expect and what to conider most. According to the records, the drivefr and fuel was most considered. This was for the reason people will be away from their convinience and should be given better allowances. According to the agencies we got the information from, there was the need to budget on more since the unexpected happens, for example an accident may occur.
Initiate | Material | Labor | Indirect Costs | Base Cost | Reserve | Total Cost | Funding Source | Cost Methodology
| 200 | 100 | 50 | 40 | 100 | 490 | Tour Agencies | invoice price of varios trips
WBS Description: The inoice cost of the previous have us a clear picture of what our trips will cost.
Cost Description: the unit cost of every itme was well documented to avoid future failures.
Planning | Material | Labor | Indirect Costs | Base Cost | Reserve | Total Cost | Funding Source | Cost Methodology
| 200 | 200 | 150 | 40 | 40 | 630 | Tour Agencies | invoice price of previous trips
WBS Description: Material description was retrived from the previous agencies involved in the trips.
Cost Description: every cost was determined by the unit cost at that particular period.
Execution | Material | Labor | Indirect Costs | Base Cost | Reserve | Total Cost | Funding Source | Cost Methodology
| 100 | 200 | 100 | 280 | 40 | 720 | Tour Agencies | invemtory valuation method
WBS Description: Every plan or project requires well detailed information on the type of expenses to be incurred when executing it including all the indirect costs.
Cost Description: The material and labor involved in the execution will involve the project executors and their labor payments.
Control | Material | Labor | Indirect Costs | Base Cost | Reserve | Total Cost | Funding Source | Cost Methodology
| 200 | 100 | 20 | 30 | 40 | 390 | Tour Agencies | invemtory valuation method
WBS Description: Regarding the road trip and the activities involved, there was the need to have a well budgeted schedule to avoid inconviniences.
Cost Description: the toytal cost will involve all the control activities regardless they will take place or not.
Close Out | Material | Labor | Indirect Costs | Base Cost | Reserve | Total Cost | Funding Source | Cost Methodology
| 40 | 30 | 50 | 30 | 60 | 210 | Tour Agencies | invemtory valuation method
WBS Description: the close out involves all the other activities to be involved at the end of the project to ensure its success.
Cost Description: There may be activities that will not use the cash despite being budgeted for. Thiss costs will be refunded to the tour agencies.
Total Budget | Material | Labor | Indirect Costs | Base Cost | Reserve | Total Cost | Funding Source | Cost Methodology
| 30 | 50 | 50 | 80 | 40 | 250 | Tour Agencies | invemtory valuation method
WBS Description: the total budget has been drawn from previous trips which has given a better pictiure of what to expect.
Cost Description: the total cost involved in the trip is what will be incurred by both the main actors and the others. The main actors will be the drivers and the travelers while the others will be tour guides in every destination.

## Gantt Chart
Gantt Project Plan Sequence
Task Item | Task Item | Preceding Activity | Activity Duration | Owner | Status | Start Date | End Date | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01
1 | Car choice for a trip | No | 7 days | Me | Not done | 2017-01-02 | 2017-01-09
2 | Documents and money preparation | No | 7 days | Me | Not done | 2017-01-02 | 2017-01-09
3 | Car purchase and preparation | Car choice for a trip | 1 day | Me | Not done | 2017-01-09 | 2017-01-09
4 | Finding and hiring a driver | Car purchase and preparation | 7 days | Me | Not done | 2017-01-09 | 2017-01-16
5 | Preparing food, clothes and other items | All above activities | 1 day | Me | Not done | 2017-01-16 | 2017-01-16
6 | Starting a trip and reaching the boarder | All above activities | 7 days | Me and driver | Not done | 2017-01-16 | 2017-01-23
7 | Preparing documents to cross the border | Starting a trip and reaching the boarder | 1 day | Me and driver | Not done | 2017-01-23 | 2017-01-23
8 | Trip through country 1 | Preparing documents to cross the border | 14 days | Me and driver | Not done | 2017-01-23 | 2017-02-06
9 | Preparing documents to cross the border | Trip through counry 1 | 1 day | Me and driver | Not done | 2017-02-06 | 2017-02-06
10 | Trip through country 2 | Preparing documents to cross the border | 14 days | Me and driver | Not done | 2017-02-06 | 2017-02-20
11 | Preparing documents to cross the border | Trip through counry 2 | 1 day | Me and driver | Not done | 2017-02-20 | 2017-02-20
12 | Trip through country 3 | Preparing documents to cross the border | 14 days | Me and driver | Not done | 2017-02-20 | 2017-03-06
13 | Returning home | All above activities | 42 days | Me and driver | Not done | 2017-03-06 | 2017-04-17

## Risk
ID | Risk Description | Probability |  | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | Fatigue | 10 | 5 | 8 | 9 | 1 | long distance driving | since it will be a trip with several people, once fatigue is detected, we shall exchange drivers | the best action is to exchnage drivers or have small rests at certain points | the person who will be sitted with the driver will be the monitor and they will exchange with someone after specified distance.
2 | Loosing the route | 4 | 8 | 3 | 10 | 2 | loosing a route might be becouse of lack of knowledge of the placing one is going and not having the map to that place or having two routes of different places that look exact the same. | anayzng the place where we want to go and ensuring one carries a map to guide us where we might forget | Incase we are lost, we shall stop and analyze the map to see where we lost our way so as to go the place and continue with the right route. | I will monitier the route becouse I best know the route to the place and when I am exhausted leave it to another person to follow the map
3 | Car breakdown | 5 | 9 | 2 | 10 | 3 | Lack of taking the car for a service before the journey | make sure the car is checked and is in a good condition before beginning the journey | If the riskhappens, it would be a big problem becouse there is no person who knows to engineer the car. | We shall make sure that we stop at every gas station for the car to be monitored