## Sheet1
System definition |  |  | Duration | Start date
1,1 | Identification of organizational goals and scope |  | 20 Days | 01.Tpa.17
| 1.1.1 | Set targets and goals | 1 week
| 1.1.2 | Defining rules and regulations | 1 week
| 1.1.3 | Organizational culture | 6 days
1.2 | Operational Feasibility |  | 14 Days
| 1.2.1 | Cost | 3 days
| 1.2.2 | Document and schedule charts and feasibility | 5days
| 1.2.3 | Technicalities and processes | 2 days
| 1.2.4 | Management decisions and reviews | 2 days
| 1.2.5 | Stakeholder lists, deliveries and processes | 2days
1.3 | Project Plan
| 1.3.1 | Establishment of milestones | 30 Days
| 1.3.2 | Creation and documentation of Work Breakdown structure(WBS) | 15 days
| 1.3.3 | Resource requirments | 15 days
|  | 1.3.3.1 Employees | 3 days
|  | 1.3.3.2.Stakeholder supply chain | 3 days
|  | 1.3.3.3 Travel expenses | 3 days
|  | 1.3.3.4 Automates payment trascations | 3 days
|  | 1.3.3.5 Knowledge based systems (database for deliveries | 3 days
1.4 | Project Team |  | 35 Days
| 1.4.1 | Meeting and discussion between theimmediate stakehoders
| 1.4.2 | Outsource IT professional for efficient delivery database system
| 1.4.3 | Develop Job descriptions and payment schemes
| 1.4.4 | Hire two delivery personnel to improve efficiency