Case Study: Project Model Part 2 Grading Rubric

| Elements | Criteria | Points Possible | Points Earned |
| --- | --- | --- | --- |
| Microsoft Project Model | The Project includes each of the required elements from the instructions (see instructions for details): - Saved as LastName_Project_Name - Overall project is first task, with info in notes. - Project start date with rationale. - At least 5 deliverables included. - At least 20–25 unique tasks included. - Hierarchy delineates deliverables and tasks. - Project coded in 1.1, 1.1.1, 1.2 format. - Duration (in days) for each task. - Justified time estimates for at least 5 tasks. - At least 3 milestones included. - All individual tasks and milestones linked. - At least 2 relationships are not Finish-to-Start. - At least 1 task includes lead or lag time, with rationale. - At least 6 human resources entered on the Resource Sheet. - At least half of the resources include comments. - Labor costs included. - Resources assigned to every task. - Over-allocation justified, if needed. - Project baseline set. - Project displayed as a network diagram. - Document submitted on time. | 150 |  |
| Total |  | 150 |  |
| Instructor’s Comments |  |  |  |