CLC - Milestones Schedule and Critical Risks Assessment for the Capstone Project

Mobile Pet grooming Business

Diana Farah, Norma Neal, Ryan Turnquist, Torey Yankton

Grand Canyon University: BUS-485

April 2, 2017

The Milestone Schedule and Critical Risks Assessment

The milestone schedule and Critical Risk assessment section will help us to understand the progress of our business, steps need to be taken, and tasks to complete, and the risk that is associated when marketing the Mobile pet grooming business.  The business plan needs to define the list of tests to be completed so we can test, and complete the tasks in a timely manner. The various tasks includes marketing the business, designing of website, mobile app, hiring and training employees, preparing the Pet mobile vans, ordering all the supplies needed, and launch date of the business.  The tasks will be completed within six months.

Preferred Timing and  Objectives

The preferred timing in the company’s business is 6 months (26 weeks) to market, and make the public aware of the business in the United States. As for the Canada launch, that will be done at the 2 year mark in order to expand first in the United States.  A good chosen and written Preferred Timing and  Objectives can direct our new business in the right direction and keep an the company on the right track to success. The company seeks to market, and release the business within the 6 months. This allows the company to achieve it's objectives and prepare everything in a timely manner. The company seeks to market products, the convenience of the service, safety of the pets, quality, and the low prices we offer. Sales tools includes pamphlets at pet product store, demos, mail coupons, and competitive positioning would be useful. Within the 6 months, the company should have marketed and released the vans to operate the business. The task list will show how our Mobile Pet Grooming business seeks to achieve it's objectives and milestone schedule.

Milestone Task List

| Mile stone | Due Date |
| --- | --- |
| Initial Capital Contribution | Completed |
| Register the Business | Week one |
| Contact an App, and Website developer | week3 |
| App and website completion | Month 5 |
| Purchase the Vans | Month one |
| get the company Logo painted on Vans | Month two |
| Interview and Hire Groomers | Month 3 |
| Get Groomers licensed if not yet | Month 5 |
| Train Groomers | Month 4 |
| Order supplies | Month 5 |
| US Launch | Month 6 |
| International Expansion, Canada Launch | 24 month |
| Develop App and website for Canada | month 20 |

Contingency Plan

- In the event that there is a problem that needs to be addressed in regards to our warehouse or a building disaster, please contact Ryan Turnquist ASAP.

- In the event of a chemical spill, or exposure to a Hazardous Chemical. Either at our warehouse or at a customer’s residence, please contact Torey Yankton. Please do not attempt to clean up the chemical spill yourself before contacting Tory. Tory will Determine if a prober cleaning crew need to clean up the spill, or you are able to follow the policies and procedure of cleaning the spill.

- In the event of a mechanical failure on our warehouse equipment please call Diana Farah to report the event, and follow the proper procedures.

- In the event of vehicle failure please call Norma Neal, and AAA.

- If you are calling out sick or are having a family emergency please call Ryan Turnquist, and try to call out two hours prior to your scheduled shift time.

- In the Event of a Personal Injury Contact Diana Farah, and go to the nearest Urgent care or ER for Medical care.

- In the Event of Clients Pet injury Contact Diana Farah, and insure the pet gets to the vet of the clients choice. Insure the customer all expenses will be covered.

- If you are dealing with a very unhappy customer please call Diana Farah for customer satisfaction in order to follow through, and retain customers.

Citations

Writer, L. G. (2011, September 28). How to Develop Milestones for Your Business. Retrieved April 02, 2017, from http://smallbusiness.chron.com/develop-milestones-business-25635.html

Setting Appropriate Milestones in an Early-Stage Startup. (n.d.). Retrieved April 02, 2017, from http://seedcamp.com/resources/setting-appropriate-milestones-in-an-early-stage-startup/