Final Examination Work File 			Name:

(Increase or decrease space as needed)

Question 1

The minimum time required to complete the project is: 25 days.

Shown below:

F,4

F,4

C,8

C,8

E,4

E,4

G,3

G,3

B,9

B,9

A, 5

A, 5

D,6

D,6

Activity A: ES-0, EF-5, LS-0, LF-5, TS-0

Activity B: ES-5, EF-14, LS-5, LF-14, TS-0

Activity C: ES-5, EF-13, LS-6, LF-14, TS-1

Activity D: ES-14, EF-20, LS-16, LF-22, TS-2

Activity E: ES-14, EF-18, LS-14, LF-18, TS-0

Activity F: ES-18, EF-22, LS-18, LF-22, TS-0

Activity G: ES-22, EF-25, LS-22, LF-25, TS-0

You must fill in the following table to support your answers to Questions 2 thru Question 6 (worth 24 points total)

| Name | ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- | --- |
| A | 0 | 5 | 0 | 5 | 0 |
| B | 5 | 16 | 5 | 16 | 0 |
| C | 5 | 14 | 7 | 16 | 2 |
| D | 5 | 14 | 11 | 21 | 7 |
| E | 16 | 23 | 18 | 25 | 2 |
| F | 16 | 21 | 16 | 21 | 0 |
| G | 21 | 25 | 21 | 25 | 0 |
| H | 25 | 31 | 25 | 31 | 0 |

Slack = LF – EF

2. The early start time (ES) for job G is: Day 21

3. The late finish time (LF) for job C is: Day 16

4. The critical path is given by: The path that has activities that have to be finished on time for the overall project to remain on schedule. They have no slack. Thus:

A → B → F → G → H

5. The minimum time required to complete the project is: 31 Days

6. The slack at activity D is: 7 days

Question 7

Optimistic Time (to) = 3 days

Most Likely Time (tm) = 6 days

Pessimistic Time (tp) = 15 days

Expected Time = (to + 4tm +tp)/6

(3+4(6) +15)/6 = 7 days

Question 8 (7 points)

Cost per order = 50 dollars

Holding cost per year = 20%

Annual Demand = 5000 units

(2*5000*50)/ 100

= 70.71

EOQ = 70 units per order

Therefore, none of the above answers are correct

Question 9 (4 points)

If EOQ = 400

Holding Cost =?

20% * 10 = 2

2*Q/2

2* 400 /2 = 400 dollars

Question 10 (3 points)

If 200 units are ordered each time, 25 orders will be placed in a year

100 * 50 = 5000

5000/200 = 25

Question 11 (4 points)

If 200 units are ordered each time, then the time between orders (in working days) is

Annual demand = 5000 units

= Q/ Annual demand (D)

Time between orders = 200/5000 years = 0.04 * 250 working days = 10.

Question 12

If 1000 are ordered each time, then what will be the total ordering cost per year = 250 dollars.

Total Ordering Cost = Number of orders * Cost per order

5000/1000 = 5

5 * 50 = 250 dollars

Question 13

Reorder point = Average Daily Usage * Lead time in days

(100/5) * (3*5) = 300 units

Question 14

= √ ((2*7500*15)/ 187.5)

= 34.64

34 units per order

Question 15

|  | Annual Usage | Unit Cost | Annual Consumption Value | Percentage | Cumulative percentage |
| --- | --- | --- | --- | --- | --- |
| Item Type | in thousands | in Dollars | In thousands of Dollars | % | % |
| Item 10 | 300 | $4.25 | 1275 | 40.47 | 40.47 |
| Item 7 | 60 | $14.25 | 855 | 27.14 | 67.61 |
| Item 3 | 20 | $16.00 | 320 | 10.16 | 77.77 |
| Item 9 | 100 | $2.75 | 275 | 8.73 | 86.50 |
| Item 8 | 22 | $10.00 | 220 | 6.98 | 93.48 |
| Item 6 | 30 | $2.50 | 75 | 2.38 | 95.86 |
| Item 5 | 20 | $3.00 | 60 | 1.90 | 97.76 |
| Item 2 | 30 | $1.25 | 37.5 | 1.19 | 98.95 |
| Item 1 | 10 | $2.50 | 25 | 0.79 | 99.74 |
| Item 4 | 10 | $0.75 | 7.5 | 0.24 | 99.98 |
| Total |  |  | 3150 | 99.98 |  |

Total Consumption value in thousands of dollars = 3150

Item 7 will be classified as an A Item

(855/3150) *100 = 27.14% of total consumption value

Question 16

Item 8 will be classified as a C Item

(220/3150) *100 = 6.98% of total consumption value

Question 17

Item 6 will be classified as a C Item

(75/3150) *100 = 2.38% of total consumption value

Question 18

A requires 3 units of B, 1 units of C, and 2 unit of D.

Number of units that can be produced by B = 45/3= 15

Number of units that can be produced by C = 50/1 = 50

Number of units that can be produced by D = 35/2 = 17

Units that can be delivered to customers = 15 + 20 = 35 Units

Question 19

The value of Entry A is:300

| Item D | 1 | 2 | 3 | 4 | 5 | 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Gross Requirements | 100 | 300 | 100 | 300 | 200 | 50 |
| On Hand/ Scheduled Receipts | 700 | 600 | 300 | 900 |  |  |
| Net Requirements |  | 300 |  | A300 |  |  |
| Planned Order Releases |  | B300 |  |  |  |  |

The net requirements at A is 300

Question 20

The value of Entry B is: 300

The planned order releases at B is 300 as shown.

Question 21

If the master schedule calls for the production of 50 units of A, 400 units of E are needed

Each A requires 2 units of B

50 units of A require (2*50) units of B. = 100

Each B requires 4 units of E

100 units of be will require (4*100) = 400 Units of E

Question 22 (5 points)

If the MPS calls for the production of 50 units of item A, 500 units of item D are needed?

Each A requires 4 units of D and 2 units of B.

To make 50 units of A, 100 units of B are required

1 unit of B requires 3 units of D

Therefore (3*100) units of D are needed to make 50 units of A.

(4*50 units of A) = 200 units of D.

Total units of D required = (300+200) = 500 units of D.

Question 23 (8 points)

20 units of A are available, therefore 30 more need to be produced.

20 units of B, 20 of D and 20 of E are available.

To produce 30 units of A,

(30*2) units of B are required = 60 but 20 are already available.

Therefore, to make 40 units of B, (3*40) units of D are required. Thus 120 units of D.

In addition, (4*30) units od D are directly required = 120

Total units of D are 240

But 20 units are already available.

Units currently required = (240-20) = 220 units.