## Crashing Problems
GIVEN INFORMATION | [5 empty] | COMPUTED INFORMATION
Activity | Pred. | Normal Duration (weeks) | Crashed Duration (weeks) | Normal Cost | Crashed Cost | Normal Duration Minus Crashed Duration | Crashed Cost Minus Normal Cost | Crash Cost Per Week | Critical Path Activity | Weeks Crashed | Total Cost
A | - | 20 | 15 | 2000 | 3000 | 5 | 1000 | 200 | Yes | 1 | 200
B | - | 11 | 8 | 1200 | 1350 | 3 | 150 | 50
C | - | 9 | 9 | 1500 | 1500 | 0 | 0 | 0
D | A, B | 6 | 4 | 1800 | 2100 | 2 | 300 | 150 | Yes | 2 | 300
E | C | 4 | 3 | 500 | 900 | 1 | 400 | 400
F | E | 8 | 6 | 500 | 600 | 2 | 100 | 50
G | D, F | 4 | 2 | 800 | 950 | 2 | 150 | 75 | Yes | 2 | 150
H | D | 2 | 1 | 500 | 1200 | 1 | 700 | 700
[10 empty] | 5 | 650
The objective was to identify the lowest crash activity per week item. The answer is G, G reduces weeks from 4 to 2.
Doing this creates two critical paths now.
A, D, H | = | 28 weeks
A, D, G | = | 28 weeks
The next step is to locate an activity, within those two critical paths, that can be reduced next to see if you can
reduce the number of weeks again.
D can be reduced from 4 to 2 and doing so reduces 28 weeks to 26 weeks.
A, D, H | = | 26 weeks
A, D, G | = | 26 weeks
The next objective is to reduce it down to 25 weeks…..
A can be reduced by 1 week which meets the objective of 25 weeks.
A, D, H | = | 25 weeks
A, D, G | = | 25 weeks

## W06 Homework_Quiz
Activity | Immediate Predecessor(s)
A | - |  | A | B | F | H
B | - |  | 3 | 8 | 9 | 5 | 25
C | -
D | A |  | A | C | F | H
E | B |  | 3 | 7 | 9 | 5 | 24
F | C
G | D |  | A | D | G | H
H | E, F |  | 3 | 9 | 11 | 5 | 28 |  |  | Critical Path
|  |  | A | E | G | H
|  |  | 3 | 6 | 11 | 5 | 25
Activity | Duration (Weeks) | Immediate Predecessor(s) |  | Activity | Time | ES | EF | LS | LF | D | Critical Path
A | 3 | - |  | A | [6 empty] | Yes
B | 8 | A |  | B
C | 7 | A |  | C
D | 9 | A |  | D | [6 empty] | Yes
E | 6 | A |  | E
F | 9 | B, C |  | F
G | 11 | D, E |  | G | [6 empty] | Yes
H | 5 | F, G |  | H | [6 empty] | Yes
What is the duration of the project (in weeks)?
What is the earliest week you could start activity H?
What is the latest week you could start activity B?
What is the slack time for activity F?
What is the latest week you could finish activity D?
What would be the overall duration of the project if activity E were increased by 2 weeks (from 6 to 8 weeks)?
What would be the overall duration of the project if B were increased by 4 weeks (form 8 to 12 weeks)?

## Sheet4
3 | 0 | 3
8 | 3 | 11
7 | 3 | 10
9 | 3 | 12
6 | 3 | 9
9 | 11 | 20
11 | 12 | 23
5 | 23 | 28

## Chart Example
Legend
N | Activity Name
ES | Earliest Start Time |  | N
EF | Earliest Finish Time
LS | Latest Start Time
LF | Latest Finish Time | ES |  | EF
D | Activity Duration
|  | LS |  | LF
D