INFS3632 Service & Quality Management

Homework #5

- This homework accounts for 8% of the total marks for this course.

- Total marks for this homework: 100 marks

- This homework is due at the beginning of the class on 23 May 2017.

- The School of ISTM requires you to submit your homework with a signed cover sheet, which can be found on Moodle.

- Submit a typed hard-copy that contains detail answers for all questions. You may write equations or draw diagram by hand if they are deemed too time-consuming to produce.

- To facilitate the instructor’s marking, you are required to submit a summary page (as shown on Page 2), which must be typed and contain no equations and diagrams. You still need to provide detailed answer for each question that the instructor will also check.

- Organise your submission as follows:

  - Signed cover page

  - Summary page

  - Detailed answers for the questions

Name:                                          .

Summary of Answers

Question 1

(a)

| Activity | ES | EF | LS | LF | Float | Critical () |
| --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |
| B |  |  |  |  |  |  |
| C |  |  |  |  |  |  |
| D |  |  |  |  |  |  |
| E |  |  |  |  |  |  |
| F |  |  |  |  |  |  |
| G |  |  |  |  |  |  |

Earliest time that the project can be completed = ?

(b) Yes/No and Why?

Question 2

(a)

| Activity | ES | EF | LS | LF | Float | Critical () |
| --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |
| B |  |  |  |  |  |  |
| C |  |  |  |  |  |  |
| D |  |  |  |  |  |  |
| E |  |  |  |  |  |  |
| F |  |  |  |  |  |  |
| G |  |  |  |  |  |  |
| H |  |  |  |  |  |  |
| I |  |  |  |  |  |  |
| J |  |  |  |  |  |  |

Earliest time that the project can be completed = ?

(b) How long and why?

(c) Which activity and why?

Question 3

| Project duration | Critical path(s) before crashing | Activities crashed | Crash cost incurred ($) |
| --- | --- | --- | --- |
| 14 13 |  |  |  |
| 13 12 |  |  |  |
| 12 11 |  |  |  |
| Total crash cost: |  |  |  |

Question 1 (30 marks)

A strategy consultancy company plans as project with a new client. The following table gives information on the activities in a project.

| Activity | A | B | C | D | E | F | G |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Duration (days) | 25 | 20 | 18 | 10 | 10 | 9 | 7 |
| Predecessors | - | - | A, B | B | D, G | D | A |

- Draw the project network diagram and perform CPM. Fill your CPM result in a table same as the following one. What is the earliest time that the project can be completed? Which activities are critical? (20 marks)

| Activity | ES | EF | LS | LF | Float | Critical () |
| --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |
| B |  |  |  |  |  |  |
| C |  |  |  |  |  |  |
| D |  |  |  |  |  |  |
| E |  |  |  |  |  |  |
| F |  |  |  |  |  |  |
| G |  |  |  |  |  |  |

- Is the project completion time altered if each activity requires one person working full time for its entire duration and there are only three employees available to work on the project? (Hint: draw a Gantt chart) (10 marks)

Question 2 (40 marks)

A publisher is planning to launch a range of handbooks designed for sale as exam aids for students. The following table describes the activities in this project with times and precedence relations.

| Activity | Duration (weeks) | Predecessors |
| --- | --- | --- |
| A | 7 | - |
| B | 5 | - |
| C | 6 | - |
| D | 12 | C |
| E | 10 | A, C |
| F | 16 | B |
| G | 15 | A, D |
| H | 18 | D, E |
| I | 9 | G, H |
| J | 20 | E, F |

- Draw the project network diagram of this project and perform CPM. Fill your CPM result in a table same as the following one. What is the earliest time that the project can be completed? Which activities are critical? (20 marks)

| Activity | ES | EF | LS | LF | Float | Critical () |
| --- | --- | --- | --- | --- | --- | --- |
| A |  |  |  |  |  |  |
| B |  |  |  |  |  |  |
| C |  |  |  |  |  |  |
| D |  |  |  |  |  |  |
| E |  |  |  |  |  |  |
| F |  |  |  |  |  |  |
| G |  |  |  |  |  |  |
| H |  |  |  |  |  |  |
| I |  |  |  |  |  |  |
| J |  |  |  |  |  |  |

- If both A and E are delayed by one week (so that their durations become 8 weeks and 11 weeks respectively), by how long, if at all, will the project as a whole be delayed? Why? (10 marks)

- Suppose that, by adding extra resources, any single activity can have its duration reduced by 5 weeks, but these extra resources can only be assigned to one activity. Explaining your reasoning, state which activity should be chosen in order to have the largest impact on project completion. (10 marks)

Question 3 (30 marks)

Ridlan Eelctronics produces a variety of medical equipment. Ridlan is proposing to build a new type of blood analysis machine, suitable for use in developing countries. The activities required to build a prototype for the new design are shown in the table below.

| Activity (Act) | Normal duration (weeks) (X) | Shortest possible duration | Cost of one week’s reduction | Predecessors |
| --- | --- | --- | --- | --- |
| A | 3 | 2 | $600 | - |
| B | 2 | 1 | $700 | - |
| C | 2 | 2 | - | - |
| D | 7 | 3 | $75 | A |
| E | 6 | 3 | $50 | B |
| F | 3 | 2 | $500 | C |
| G | 4 | 2 | $150 | D, E |

The project network diagram is shown in the following figure with the CPM result.

2

E

8

4

6

10

START

FINISH

10

G

14

10

4

14

0

B

2

2

2

4

0

A

3

0

3

3

3

D

10

3

7

10

2

F

5

11

3

14

0

C

2

9

2

11

14

$150

$500

$700

$75

$600

Legend

ES

LS

Act

X

EF

LF

Suppose that there is a trade show in 11 weeks time. Based on the project costs, you are asked to determine the most cost-effective way to reduce the project duration to 11 weeks to finish the prototype in time. Perform activity crashing to shorten the project duration by one week at a time sequentially.  Summarise your answer in a table similar to the following one. (30 marks)

| Project duration | Critical path(s) before crashing | Activities crashed | Crash cost incurred ($) |
| --- | --- | --- | --- |
| 14 13 |  |  |  |
| 13 12 |  |  |  |
| 12 11 |  |  |  |
| Total crash cost: |  |  |  |