PROBLEMS

Problem 1: Find the schedule and cost variances for a project that has an actual cost at month 22 of $540,000, a scheduled cost of $523,000, and an earned value of $535,000.

($000)

| Month | AC | PV | EV |
| --- | --- | --- | --- |
| 22 | $540 | $523 | $535 |
| CV |  | Favorable or Unfav? |  |
| SV |  | Favorable or Unfav? |  |

Problem 2: A sales project at month 5 had an actual cost of $34,000, a planned cost of $42,000, and a value completed of $39,000. Find the cost and schedule variances and the CPI and SPI.

($000)

| Month | AC | PV | EV |
| --- | --- | --- | --- |
| 5 | $34 | $42 | $39 |
| CV |  | Favorable or Unfav? |  |
| CPI |  |  |  |
| SV |  | Favorable or Unfav? |  |
| SPI |  |  |  |

Problem 3: A software development project at day 70 exhibits an actual cost of $78,000 and a scheduled cost of $84,000. The software manager estimates a value completed of $81,000. What are the cost and schedule variances and CSI? Estimate the time variance.

($000)

| Day | AC | PV | EV |
| --- | --- | --- | --- |
| 70 | $78 | $84 | $81 |
| CV |  | Favorable or Unfav? |  |
| CPI |  |  |  |
| SV |  | Favorable or Unfav? |  |
| SPI |  |  |  |
| CSI |  | On target? |  |
| TV |  | Delayed or on time? |  |

Problem 4: A project to develop a county park has an actual cost in month 17 of $350,000, a planned cost of $475,000, and a value completed of $300,000. Find the cost and schedule variances and the three indexes.

($000)

| Month | AC | PV | EV |
| --- | --- | --- | --- |
| 17 | $350 | $475 | $300 |
| CV |  | Favorable or Unfav? |  |
| CPI |  |  |  |
| SV |  | Favorable or Unfav? |  |
| SPI |  |  |  |
| CSI |  | Favorable or Unfav? |  |