From the data shown below, calculate the earned value of each control account as of 5/30/14. Assume all control account work is on schedule except as noted below.

| Control Account | Scheduled Start | Scheduled Completion | Budgeted Value | EV Progress Rule |
| --- | --- | --- | --- | --- |
| 1 | 3/3/2014 | 6/30/2014 | 11,500 | Percent Complete with Gates (Note 1) |
| 2 | 5/5/2014 | 6/6/2014 | 3,500 | Fixed Formula: 50/50 |
| 3 | 5/26/2014 | 6/6/2014 | 1,250 | Fixed Formula: 0/100 |
| 4 | 5/12/2014 | 5/30/2014 | 2,450 | Fixed Formula: 30/70 |
| 5 | 4/14/2014 | 7/11/2014 | 16,800 | Weighted Milestones (Note 2) |

Note (1): Five equally-valued gates have been established in this control account. Two of the five gates are complete as of 5/30/14. The Control Account Manager estimates that half of the work required for the third gate has also been completed.

Note 2: Six milestones have been established in this control account with the following values: (1) milestone 1 – 20%; milestone 2- 15%; milestone 3 – 10%; milestone 4 – 25%; milestone 5 - 15%; milestone 6 – 15%. Three of the milestones are complete as of 5/30/14.