Remodeling the Dining Area

Week 2 Assignment

Project Charter

Project Charter: Remodeling the Dining Area

Project Sponsor: Unknown Created: March, 2017

Project Manager: Joe Black Date Updated: March 21, 2017

1.0 Background

The project involves remodeling a portion of the house that covers the dining area and the sitting room. The aim of remodeling is to allow an elegant design and also create space for more people. The project plan will cover the major deliverables in the project, activities, tasks, cost, budgets, and the time required.

2.0 Objective

- Research on the different policy options viable for the project

- Complete the policy document

- Design drawings

- Design review

- New furniture

- New water channels

3.0 Project Scope

The remodeling of the dining area project will start its operations on 3/25/17 which will start by outlaying the key activities that important to ensure that the foundation of the design is well formulated these activities include

a.	Review of the project

b.	Environmental audit

c.	Budgeting

d.	Demolition

e.	Purchases and Transport

f.	Installations

4.0 Key Resources

- Windstar consultants

- Speed Val limited

- Oyster limited

- Quarter International

- Thread restaurant

- FINE & kish  Limited

5.0 Project Milestones

- Review of the project -	3/23/2017

- Environmental audit -3/23/2017

- Budgeting -3/23/2017

- Demolition -3/24/2017

- Purchases and Transport -3/25/2017

- Installations-3/26/1017

- Remodeling Area -3/28/2017

- Finishing -3/30/2017

- Occupation of the dining area-4/4/2017

6.0 Project Budget

| Task | Cost | Budget | Time |
| --- | --- | --- | --- |
| - Dining Remodeling ideas | $50 | $40 | 2 days |
| - Environmental audit | $200 | $147 | 1 day |
| - Decoration ideas | $50 | $47 | 1 day |
| - Allocation of the budget/Accounting | $245 | $231 | 3 days |
| - Removing the floor and the carpet | $ 25 | $20 | 1 day |
| - Removal of the air conditioning | $40 | $40 | 1 day |
| - Removal of water pipes | $40 | $40 | 1 day |
| - Removal of the old furniture | $40 | $40 | 1 day |
| - Hiring excavators | $40 | $40 | 1 day |
| - Demolition of the old dining and sitting area | $100 | $100 | 2 days |
| - Purchase of bricks for construction | $500 | $470 | 2 days |
| - Purchase of cement | $399 | $420 | 1 day |
| - Transport of the cement | $60 | $50 | 1 day |
| - Purchase of the metal bars | $250 | $249 | 1 day |
| - Transport of the metal bars | $40 | $42 | 1 day |
| - Transport of the bricks | $36 | $40 | 1 day |
| - Quantity survey | $200 | $250 | 1 day |
| - Construction permit | $0 | $0 | 1 day |
| - Purchasing the new dining table | $200 | $180 | 1 day |
| - Purchasing the ventilators | $120 | $140 | 1 day |
| - Transportation of the supplies | $40 | $42 | 1 day |
| - Installation of wall insulators roof and the gutter | $40 | $40 | 3 day |
| - Purchase and transport of the heat thermals | $200 | $205 | 1 day |
| - Installation of the heat thermals | $40 | $26 | 2 days |
| - Purchasing and transportation of the wooden ceilings | $120 |  | 1 day |
| - Installation of the celling | $43 | $40 | 2 days |
| - Hanging of the interior doors | $40 | $43 | 1 day |
| - Purchase and transport of the door lock and security system | $120 | $132 | 1 day |
| - Installation of the door lock and security system | $45 | $40 | 1 day |
| - Purchase and transport of the replacement windows | $120 | $113 | 1 day |
| - Replacement of the windows | $40 | $38 | 1 day |
| - Installation of molding wood paint | $44 | $40 | 1 day |
| - Purchase and transport of the interior design materials | $120 | $147 | 1 day |
| - Interior designing | $200 | $180 | 4 days |
| - Purchase and transportation of the paint | $40 | $ 45 | 1 day |
| - Painting of the dining and sitting area | $100 | $120 | 2 days |
| - Installation of the fire extinguishers | $69 | $70 | 2 days |
| - Arrangement of the labor including hiring | $200 | $250 | 2 days |
| - Purchase of the wood and nails for the cabinets | $120 | $ 100 | 1 day |
| - Transport of the wood and nails | $40 | $40 | 1 day |
| - Re-facing of the dining cabinets | $180 | $180 | 2 days |
| - Purchase of new dinning crockery | $120 | $234 | 1 day |
| - Purchase and transport of the wooden floor | $40 | $40 | 1 day |
| - Installation of the wooden floor | $30 | $32 | 2 days |
| - Purchase and transport of the water channels | $120 | $100 | 1 day |
| - Installation of the water channels | $49 | $49 | 2 days |
| - Purchase and transport of the new lighting | $120 | $100 | 1 day |
| - Installation of new lighting | $ 123 | $132 | 1 day |
| - Purchase of fans | $120 | $ 120 | 1 day |
| - Installation of the fans | $40 | $40 | 2 days |
| - Arrangement and positioning of the dining equipment | $20 | $22 | 2 days |
| - Installation of the lighting switches | $20 | $30 | 2 days |
| - Insulate attic | $40 | $40 | 1 day |
| - Purchase of fire alarms | $120 | $ 130 | 1 day |
| - Installation of the fire alarms | $67 | $70 | 2 days |
| - Purchase and installation of door curtains | $120 | $ 130 | 2 days |
| - Installation of water dispenser | $40 | $40 | 1 day |
| - Purchase and installation of veranda tiles - Exterior finishing of the corridors | $120 $ 80 | $130 $100 | 3 days 2 days |
| - Final walk through | $55 | $ 50 | 1 days |

7.0 Risks

- Donor fatigue

- Unreliable volunteers

- Low turnout

- Cost overrun

- Vendors do not have the capacity to support the even

- Legal constraints due to compliance

References:

Brones, F., de Carvalho, M. M., & de Senzi Zancul, E. (2014). Ecodesign in project management: a missing link for the integration of sustainability in product development? Journal of Cleaner Production, 80, 106-118.

Cassidy, N., Galvin, L., Dunne, D., & Egan, J. (2016). Development of a national patient charter for idiopathic pulmonary fibrosis.

Golini, R., & Landoni, P. (2014). International development projects by non-governmental organizations: an evaluation of the need for specific project management and appraisal tools. Impact Assessment and Project Appraisal, 32(2), 121-135.

Sellers, M. M., Hanson, K., Schuller, M., Sherman, K., Kelz, R. R., Fryer, J., ... & Bilimoria, K. Y. (2013). Development and participant assessment of a practical quality improvement educational initiative for surgical residents. Journal of the American College of Surgeons, 216(6), 1207-1213.