## Project Charter
Project ID TBD | Reduce Falls From Height Exposures | [8 empty] | Project Charter 2/20/15
SECTION 1: Project Summary
Concept Definition | Develop strategies to control ACME's employee exposures to falls from heights, including roofs.
Program | ES&H Management System |  |  |  | Project Lead(s) |  | Mike Miller
Exec. Sponsor | Krista Applegate |  |  |  | Sponsor |  | Ted Jones
SECTION 2: Vision Alignment
Problem Statement | Over 200 employees are exposed to falls from heights, and most injuries result from falls off ladders or roofs. Over the past 10 years, there have been 94 falls from heights, with at least 7 falls occurring every year. The direct cost of these accidents is $1,232,000. ACME's existing fall prevention guidelines are non-specific .
SMART Goasl (or Objective) | By 10/31/15, reduce employee exposures to falls from ladders and roofs by developing specific ladder climbing and roof access guidelines and criteria.
Expected Business Outcomes | 1. Reduction of claims frequency and severity by at least 25% via avoidance of exposure. 2. Objective guidance for employees to use when assessing risk of personal safety. 3. Improve roofing job completion cycle time by reducing downtime associated with accidents. 4. Enhanced employee satisfaction from increased awareness and control over personal safety.
Budget | $10,000 budget established for external safety consultant to assist in stakeholder assessment and identification of best practices. |  |  |  |  | Measurable Benefit & Key Metrics |  | Reduce accident frequency and severity each by 25% YOY from 2014 to 2015.
Scope | Includes: 1. Guidelines apply to all ACME labor positions, including regional sales specialists. 2. Incorporating guidelines into ACME new employee and subcontractor orientation programs. |  |  |  |  | Excludes: 1. All other ACME subsidiaries, including concrete. 2. JHA for ACME Roofers (previously completed)
SECTION 3: Execution Detail
Approach Overview | Using a "bottom up" approach. Assembling a group of 12 primary stakeholders (i.e. roofing laborers) to serve as SMEs and develop the guidelines. Outcome of group's efforts will be presented to ACME Leadership Team.
Dependencies / Risks | No dependencies. Two significant project risks: 1. Lack of consistent execution of guidelines across ACME footprint. 2. Individual laborers may be unwilling to adopt and follow new guidelines.
Forecasted Key Milestone Schedule | Activity |  |  | Date | Team Members |  | Name |  | Role
| Charter Approved |  |  | 2015-02-20 |  |  | Amy Daniels |  | Broker - SME
| Consensus on Guidelines |  |  | 2015-03-18 |  |  | Cathy Kidding |  | Change Mgmt. Consultant
| Proposal to Leadership |  |  | 2015-03-30 |  |  | Brian Walters |  | Legal Review
| Approval of Guidelines |  |  | 2015-04-17 |  |  | Roofers - Laborers* |  | SMEs (5)
| Implement Communication |  |  | 2015-04-27
| Complete Field Audits |  |  | 2015-09-30
| Project Completion |  |  | 2015-10-31
SECTION 4: Change Management Assessment (High-Level)
Audience |  | Impact |  |  |  |  | Concern(s)
Roofers - Laborers |  | High |  |  |  |  | Mindset: "I'm not afraid to climb on a roof"
Roofing Job Foremen |  | High |  |  |  |  | Higher expenses & decreased production
Customers |  | Med |  |  |  |  | Perceived delays in completing job
* Labor SMEs: | Eddie Ackers |  | Mike Sanchez
| Greg Baker |  | Ted Zinna
Chris Carter