## Sheet1
TASK | WEEKS
Purchase Land | 2
Specify Furniture for both heavy and light assisted units | 2
Develop conceptual design for faculty | 5
Final Inspecton and approval | 2
Paint and final finishes | 4
Underground utilities installed | 10
detail design for facility reviewed and approved | 12
Bid furniture | 4
Install Furniture | 2
Construction bid preparation | 4
ground Breaking and earthworks | 3
construction bid advertised and bids submitted | 5
foundation | 6
exterior walls erected | 16
Interior walls erected | 20
Plumbing installed | 14
construction bids reviewed and contract awarded | 3
roof installed | 12
electrical wring installed | 10
HVAC installed | 8