## Event Management Course Project

Listen

## Objective

To use concepts learned in this class to develop a real world event plan.

Listen

## Guidelines

Due Thursday of Week 7

Members of the class are required to prepare a complete Event Plan based on one of the event scenarios listed in the Exercises in Professional Event Coordination in the textbook.

- Review the Exercises in Professional Event Coordination in Chapters 1 through 14 of Professional Event Coordination. Select one event scenario from any of those listed in the Exercises in Professional Event Coordination in Chapters 1 through 14.

- In Week 2 of the course, you must submit a one-page topic proposal for your Final Project Event Scenario selection. The topic proposal will not be graded. This proposal will be reviewed and suggestions will be made where applicable before the Instructor approves the topic and the scope of the proposed paper. Failure to submit your proposal on a timely basis will result in a 5-point deduction from the final project grade.

- Below is an outline of the event plan. Make sure you include all necessary components with the final plan. Invent specifications for any specifications not explicitly included in the event scenario. Completed Worksheets must be included as supporting materials.

- In Week 5 of the course, a rough draft will be due. The drafts will not be graded, but will contain recommendations to incorporate into your final project. Failure to submit your draft on a timely basis will result in a 5-point deduction from the final project grade.

- All papers will be run through turnitin.com, DeVry's plagiarism software. It is imperative that you cite all sources and that your original content, i.e. your own words, make up at least 80% of your paper. Refer to the policy tab in the course for details on the DeVry plagiarism policy.

The course paper will be at least 15 pages in length (excluding any appendices) on a topic related to the theme of Event Planning and Management. Within this broad theme, the course paper is intended to be an opportunity to explore in some depth a topic related to the course that is of specific significance to you. The course paper is more a product of your critical and imaginative thinking supported by course material and related resources (including current articles) than it is a project in library research.

Following is a summary of the sections that should be included in your paper and the potential points for each section. This paper is worth 150 points total.

1. Title Page Include the title of your course paper, your name, e-mail address, school name, instructor's name, date of submittal, and class (HOSP590).

Introduction (10 Points) Describe the event scenario that you have selected and identify why it is significant. Present any background or facts that will enable the reader to clearly understand the issues. Write this like an Executive Summary in a Business Plan and include highlights of all important points. Assume the reader will not read beyond the introduction so it is imperative this part is concise, factual, and interesting.

2. Stakeholders (10 Points) Identify the stakeholders with this event and list at least two different goals that they may have. Suggest ways to meet these goals.

3. Event Theme (10 Points) Working with the event, stakeholders, and goals as described, chose a theme for this event. Explain why you choose that theme and how it supports the goals of the event.

4. Location Analysis (10 points) Pick a location for this event. The location must have a webpage with floor plans that you can link to. Using the Location check sheet, complete an analysis of the location and determine how it will support the goals of the event.

5. Anticipation (10 Points) Describe your plan for this section of the event. Include any collateral that you will create for this part. Include elements of the themes, and describe how it meets the event goals.

6. Pre-Arrival (10 Points) Describe how you will set this event. Include a timeline which works backwards from the start time detailing the load-in factors, and setup times. You must note who is going to do the work.

7. Arrival (10 Points) Describe your plan for this section of the event. Include any collateral that you will create for this part. Include the details of how people will arrive, transportation, and registration elements. Make sure that this section matches the theme and describe how it meets the event goals.

8. Atmosphere (10 Points) Describe your plan for this section of the event. Include a detailed description of décor and other technological elements. When you are working with the Location Analysis from above, plot out your floor plan for this event.

9. Appetite (10 Points) Your event must serve food of some kind. Describe your plan for this portion of the event. Detail your menu, kitchen, and serving requirements. Create a check sheet to bid this event for outside caterers. Create a list, and show pictures if possible of your table top décor, serving lines, and other necessary components to serve the food. Use your location floor plan to show where you will set up the kitchens, and serve the food. In this section, include who will be eating and how the bill will be handled.

10. Activities (10 Points) Your event must have some type of activity. Describe your plan for this portion of the event. Detail what the activities are, and what you require for this event to happen. Create a list of all necessary components, and use the location floor plan to show where this event will take place.

11. Amenities (10 Points) Every participant must receive an amenity. You can create different categories for the amenities such as spectators receive one type of amenity and participants receive another. Describe your amenities in detail. Describe how and when each attendee will receive his or her amenity.

12. After Event (10 Points) Describe how you will manage the breakdown and cleaning of this event. Include a timeline describing the load out times.

13. Final Report For Client (10 Points) Include a format for an after event review of your event. NOTE: You are not reviewing the fictitious event, but rather creating a reference that you will use to evaluate how it went. Include all necessary details for this review.

14. Budget & Financials (10 Points) Include a rough, but realistic budget for this event. Include an analysis of where you are spending your money, and how you will fund this event. Also include a copy of the bill you will submit to your client. Discuss how you will make a profit and what financial risks you will incur with this event. Also include how you will pay each vendor.

15. Reference Page (10 Points) You must use no fewer than six resources outside your textbook that have an author. Use APA formatting and cite all sources, including the text. All references must be cited in the body of your work and on your reference list. Refer to the course materials in "Student Resources" for help with APA style. Citing an author's work within your text documents your research, identifies the source for readers, and enables readers to locate the source of information in the alphabetical reference list at the end of the paper. To use the ideas or words of another person without crediting the source is plagiarism. Plagiarism in its purest form involves copying passages either verbatim or nearly verbatim, with no direct acknowledgment of the source. The most common (and unconscious) form of plagiarism is to paraphrase a direct quotation. Paraphrasing does not relieve you of the obligation to provide proper identification of source data. The best way to avoid plagiarism is to make sure all quotes, ideas, or conclusions not your own are given proper acknowledgment in your text.

- All DeVry University policies are in effect including the plagiarism policy.

- Papers are due in Week 7 of this course.

- Any questions about this paper may be discussed in the weekly Q&A Discussion topic.

- This paper is worth 150 total points and will be graded on quality of research topic, quality of paper information, use of citations, grammar, and sentence structure.

- This paper must be at least 3,000 words and 15 pages in length. Points will be deducted if the paper falls short of this requirement.

- Use APA Style, 12 point font, double spaced.

- Include all 15 sections.

Milestones

- Week 2: One page topic selection and overview is due in the Dropbox.

- Week 5: Rough draft is due in the Dropbox.

- Week 7: Final paper is due in the Dropbox.

Listen

## Grading Rubrics

| Category | Points | % | Description |
| --- | --- | --- | --- |
| Title page | 0 | 0% | Include the title of your course paper, your name, e-mail address, school name, instructor's name, date of submittal, and class (HOSP590). |
| Introduction | 10 | 7% | Describe the event scenario that you have selected and identify why it is significant. Present any background or facts that will enable the reader to clearly understand the issues. |
| Stakeholders | 10 | 7% | Identify the stakeholders with this event and list at least two different goals that they may have. Suggest ways to meet these goals. |
| Event Theme | 10 | 7% | Working with the event, stakeholders, and goals as described, choose a theme for this event. Explain why you choose that theme and how it supports the goals of the event. |
| Location Analysis | 10 | 7% | Pick a location for this event. The location must have a webpage with floor plans that you can link to. Using the Location check sheet, complete an analysis of the location and determine how it will support the goals of the event. |
| Anticipation | 10 | 7% | Describe your plan for this section of the event. Include any collateral that you will create for this part. Include elements of the themes, and describe how it meets the event goals. |
| Pre-Arrival | 10 | 7% | Describe how you will set this event. Include a timeline which works backwards from the start time detailing the load-in factors, and setup times. You must note who is going to do the work. |
| Arrival | 10 | 7% | Describe your plan for this section of the event. Include any collateral that you will create for this part. Include the details of how people will arrive, transportation, and registration elements. Make sure that this section matches the theme and describe how it meets the event goals. |
| Atmosphere | 10 | 7% | Describe your plan for this section of the event. Include a detailed description of décor and other technological elements. Working with the Location Analysis from above, plot out your floor plan for this event. |
| Appetite | 10 | 7% | Your event must serve food of some kind. Describe your plan for this portion of the event. Detail your menu, kitchen, and serving requirements. Create a check sheet to bid this event for outside caterers. Create a list, and show pictures if possible of your table top décor, serving lines, and other necessary components to serve the food. Use your location floor plan to show where you will set up the kitchens, and serve the food. In this section, include who will be eating and how the bill will be handled. |
| Activities | 10 | 7% | Your event must have some type of activity. Describe your plan for this portion of the event. Detail what the activities are, and what you require for this event to happen. Create a list of all necessary components, and use the location floor plan to show where this event will take place. |
| Amenities | 10 | 7% | Every participant must receive an amenity. You can create different categories for the amenities such as spectators receive one type of amenity and participants receive another. Describe your amenities in detail. Describe how and when each attendee will receive their amenity. |
| After Event | 10 | 7% | Describe how you will manage the breakdown and cleaning of this event. Include a timeline describing the load out times. |
| Final Report | 10 | 7% | Include a format for an after event review of your event. NOTE: You are not reviewing the fictitious event, but rather creating a reference that you will use to evaluate how it went. Include all necessary details for this review. |
| Budget | 10 | 7% | Include a rough, but realistic budget for this event. Include an analysis of where you are spending your money, and how you will fund this event. |
| References | 10 | 7% | Use and Appendix for your references. You must use no fewer than six resources outside your textbook. Cite all sources, including the text. |
| Total | 150 | 100% | A quality paper will meet or exceed all of the above requirements. |

Listen

## Best Practices

The following are the best practices in preparing this paper.

- Apply a three step process of writing… Plan, Write, and Complete.

- Prepare an outline of your research paper before you go forward.

- Complete a first draft and then go back to edit, evaluate, and make any changes required.

- Use visual communication to further clarify and support the written part of your report. You could use example graphs, diagrams, photographs, flowcharts, maps, drawings, animation, video clips, pictograms, tables, and Gantt charts.

I selected for the event management course project is “ Colleges annual fest”

Introduction

The event scenario being selected for the event management course project is college annual fest. This is an event for which students of different colleges eagerly wait for. The college annual fest offers a platform to students to display their talents and it is mostly full of fun and frolic.

College annual fest comprise of many small event that gives students an ability to reveal their talents and to have fun through different activities. These fests also act as acid test for judging the managerial skills of students and also the suppleness of decision making of the faculty members.

For the successful organization of any college annual fest it is very important to have a core committee. This core committee is composed of representative students from different branches and the faculty members. The students are the ones who perform all task and the teachers guide them for it (Shone & Parry, 2004).

Students are responsible for performing the administrative, logistical and the creative part of fest. Even in such fest, the complete power of approval lies in the hands of the faculty member who heads the committee organizing the fest. Teachers and students inform the participants of all the activities that are going to be performed in the fest.

College annual fest is mostly a source of fun and learning. Such events mainly consist of various inter college competitions especially organized to increase interactivity between students. The fest will be a two day college festival. It will be an initiative of the college and will be one of its kinds in the city. It will be organized from the noon till midnight on both days. A grand price will be given to that college which will receive the highest points in the entire event.

Each of the events will have some points associated with it. The entry in the fest will be purely on the basis of passes. Several colleges from other places will be invited to participate in the fest. A greater number of participating students is being expected for the event. The head council for the fest will take all important decisions like the allocation of funds to each and every activity (Shone & Parry, 2004).

The event will be publicized. A chief guest will be invited for the inauguration of the fest. There will be judges to judge the performance of the participants in each and every event being organized. Invites will be sent to colleges which will give them information about the date, timings and venue of the event. The event will also have sponsors for promotion.