23)	General Foundry’s project crashing data are shown in Table 9. Crash this project to 13 weeks using CPM. What are the final times for each activity after crashing?

NORMAL CRASH

NORMAL  	CRASH		COST		COST  		 IMMEDIATE

ACTIVITY 	TIME		 TIME		  ($)		  ($)		PREDECESSORS

A		3		2		1,000		1,600			-

B		2		1		2,000		2,700			-

C		1		1		300		300			-

D		7		3		1,300		1,600			A

E		6		3		850		1,000			B

F		2		1		4,000		5,000			C

G		4		2		1,500		2,000			D, E