Wedding Ceremony

| Level | WBS Code | Activity |
| --- | --- | --- |
| 1 | 1 | Wedding |
| 2 | 1.1 | Invite Guests |
| 3 | 1.1.1 | Select Important guests |
| 3 | 1.1.2 | Select General Guests |
| 4 | 1.1.1.1 | Notify them via Email |
| 4 | 1.1.1.2 | Notify them via texts and Phone Calls |
| 4 | 1.1.2.1 | Notify them Via Email |
| 4 | 1.1.2.1 | Notify them Via texts and Calls |
| 2 | 2.1 | Sign a contract for reception facility |
| 3 | 2.1.1 | Look for a good reception facility |
| 3 | 2.1.2 | Find a team to help with the search |
| 4 | 2.1.1.1 | Seek views regarding the place |
| 4 | 2.1.1.2 | Book the place |
| 4 | 2.1.2.1 | Select a witness from the team |
| 4 | 2.1.2.2 | Sign the contract with the member present. |
| 2 | 3.1 | Provide decors for the wedding |
| 3 | 3.1.1 | Look for the theme of the wedding |
| 3 | 3.1.2 | Enquire from the couple regarding the theme of the wedding |
| 4 | 3.1.1.1 | Research themes online |
| 4 | 3.1.1.2 | Use themes based on one’s own experience |
| 4 | 3.1.2.1 | Ask for their best colors |
| 4 | 3.1.2.2 | Ask the amount they have to support the variety of colors they will need at the wedding. |
| 2 | 4.1 | Provide food and beverages |
| 3 | 4.1.1 | Make a list of needed food and beverages |
| 3 | 4.1.2 | Make a list of guests with special dietary needs |
| 4 | 4.1.1.1 | Call the suppliers |
| 4 | 4.1.1.2 | Receive the deliveries |
| 4 | 4.1.2.1 | Send an email to them asking them their needs |
| 4 | 4.1.2.2 | Confirm their number before making deliveries. |
| 2 | 5.1 | Arrange for transport for visitors |
| 3 | 5.1.1 | Create a list with destination of persons and numbers |
| 3 | 5.1.2 | Search for a cheap car hire company |
| 4 | 5.1.1.1 | Set pick up time |
| 4 | 5.1.1.2 | Inform the guests of the travel arrangements |
| 4 | 5.1.2.1 | Confirm the number of people to be transported and the costs. |
| 4 | 5.1.2.2 | Pay for the costs |