Exercise 7-12:  A certification program consists of a series of activities that must be accomplished in a certain order. The activities, their immediate predecessors, and estimated durations appear in the following table.

ACTIVITY        IMMEDIATE              TIME

PREDECESSORS             (days)

A                                 —                    2

B                                 —                    5

C                                —                    1

D                                  B                    10

E                                A, D                3

F                                C                     6

G                                E, F                 8

(a) Develop a project network for the certification program.

(b) Determine the EST, EFT, LST, LFT, and slack for each activity. Also determine the total pro- gram completion time and the critical path(s).

Exercise 7-14

Exercise 7-16: