## Sheet1
Wireless Design Project
Task ID | Task Description | Start Date | End Date | Dependencies | Owner | % Complete
1 | Proposal | 2017-06-20 | 2017-07-10 | 1.2, 1.3, 1.4, 1.5 | Dave Pryor | 0%
1.2 | Logical Network Design | 2017-06-20 | 2017-06-26 | n/a | Eddie Paddington | 0%
1.3 | Physical Network Design | 2017-06-27 | 2017-07-03 | 1.2 | Brian Stahl | 0%
1.4 | Comprehensive Network Design | 2017-07-04 | 2017-07-10 | 1.3 | Felix Bapono | 0%
1.5 | Written Portion | 2017-06-20 | 2017-07-10 |  | Zhorzh Bederyan | 0%
1.2 | Logical Network Design | 2017-06-20 | 2017-06-26 |  | Eddie Pddington | 0%
1.2.1 | Identifying Customer Design Requirements |  |  |  |  | 0%
1.2.2 | Characterizing the Existing Network |  |  |  |  | 0%
1.2.3 | Physical Network Topology |  |  |  |  | 0%
1.3 | Physical Network Design | 2017-06-27 | 2017-07-03 |  | Brin Stahl | 0%
1.3.1 | Identify network components |  |  |  |  | 0%
1.3.2 | Identify Cabling |  |  |  |  | 0%
1.3.3 | Identify network topology and why |  |  |  |  | 0%
1.3.4 | Create Diagram
1.4 | Comprehensive Network Design | 2017-07-04 | 2017-07-10 |  | Felix Bapono | 0%
1.4.1 | Show recommended access points |  |  |  |  | 0%
1.4.2 | Create security suggestions |  |  |  |  | 0%
1.5 | Written Portion | 2017-06-20 | 2017-07-10 |  | Zhorzh Bederyn | 0%
1.5.1 | Create Graphic Timeline |  |  |  |  | 0%
1.5.2 | Explain Security Plan |  |  | 1.4.2 |  | 0%
1.5.3 | Include topology design |  |  | 1.3.3 |  | 0%