Begin with the tables you created in Homework 4. Create a query that displays the following information for the project with PROJECT_ID=4. Pretend that the current date is 2017-01-20

- Activity Name

- Planned Start Date (Start)

- Planned Finish Date (Start plus Plan Duration)

- Percent Complete

- Planned Percent Complete (percentage of duration that has passed, assuming the current date is 2017-01-20)

- Earned Value (Estimated Cost multiplied by Percent Complete)

- Actual Cost (sum of quantity in Resource Consume multiplied by Cost Per Unit in Resource)

- Planned Value (Planned Percent Complete multiplied by Estimated Cost)

- Cost Variance (Earned Value minus Actual Cost)

- Schedule Variance (Earned Value minus Planned Value)

- Cost Performance Index (Earned Value divided by Actual Cost)

- Schedule Performance Index (Earned Value divided by Planned Value)

HOMEWORK 4:

CREATE TABLE PROJECT

(

PROJECT_ID SMALLINT NOT NULL,

PROJECT_NAME VARCHAR(35) NOT NULL,

WBS_FINALIZED BOOLEAN NOT NULL,

WP_ID SMALLINT NOT NULL,

PRIMARY KEY (PROJECT_ID),

UNIQUE KEY (PROJECT_ID));

CREATE TABLE ACTIVITY

(

ACTIVITY_ID SMALLINT NOT NULL UNIQUE,

PROJECT_ID SMALLINT NOT NULL,

ACTIVITY_NAME VARCHAR(50) NOT NULL,

START_DATE DATE NOT NULL,

PLAN_DURATION SMALLINT NOT NULL,

WBS_ID SMALLINT NOT NULL,

PARENT_ID SMALLINT,

DISPLAY_ORDER INT,

ACTUAL_START DATE,

ACTUAL_END DATE,

PERCENT_COMPLETE DECIMAL(3,1),

PRIMARY KEY (ACTIVITY_ID),

FOREIGN KEY (PROJECT_ID) REFERENCES PROJECT(PROJECT_ID) ON UPDATE CASCADE);

CREATE TABLE RESOURCE

(

RESOURCE_ID SMALLINT NOT NULL UNIQUE,

PROJECT_ID SMALLINT NOT NULL,

RESROUCE_NAME VARCHAR(20) NOT NULL,

MEASUREMENT VARCHAR(10),

COST_PER_UNIT INT NOT NULL,

PRIMARY KEY (RESOURCE_ID),

FOREIGN KEY (PROJECT_ID) REFERENCES PROJECT(PROJECT_ID) ON UPDATE CASCADE );

CREATE TABLE ACTIVITY_RESOURCE

(

AR_ID SMALLINT NOT NULL UNIQUE,

ACTIVITY_ID SMALLINT NOT NULL,

RESOURCE_ID SMALLINT NOT NULL,

DESCRIPTION VARCHAR(35),

PLAN_QUANTITY SMALLINT NOT NULL,

PRIMARY KEY (AR_ID),

FOREIGN KEY (ACTIVITY_ID) REFERENCES ACTIVITY(ACTIVITY_ID) ON UPDATE CASCADE,

FOREIGN KEY (RESOURCE_ID) REFERENCES RESOURCE(RESOURCE_ID) ON UPDATE CASCADE );

CREATE TABLE RESOURCE_CONSUME

(

RC_ID SMALLINT NOT NULL UNIQUE,

AR_ID SMALLINT NOT NULL,

QUANTITY DECIMAL(9,1) NOT NULL,

CONSUME_DATE DATE NOT NULL,

PRIMARY KEY (RC_ID),

FOREIGN KEY (AR_ID) REFERENCES ACTIVITY_RESOURCE(AR_ID) ON UPDATE CASCADE );

/* PROJECT ROWS 			*/

INSERT INTO PROJECT VALUES (4,'Process Improvement',1,2);

INSERT INTO PROJECT VALUES (7,'NM Fashion Migration',1,2);

INSERT INTO PROJECT VALUES (9,'Apple TV Project',1,15);

/* ACTIVITY ROWS			*/

INSERT INTO ACTIVITY VALUES (7,4,'Create Procedures','2017-01-01',7,8,0,NULL,'2017-01-01','2017-01-11',1);

INSERT INTO ACTIVITY VALUES (8,4,'Create Software','2017-01-08',7,9,0,NULL,'2017-01-09','2017-01-16',1);

INSERT INTO ACTIVITY VALUES (9,4,'Implement Procedures and Software','2017-01-15',14,10,0,NULL,'2017-01-16','0000-00-00',0.1);

INSERT INTO ACTIVITY VALUES (14,7,'Create Test Cases','2017-01-26',7,15,0,NULL,'2017-01-26','2017-02-12',1);

INSERT INTO ACTIVITY VALUES (15,7,'Move to live site','2017-03-02',7,16,0,NULL,NULL,NULL,NULL);

INSERT INTO ACTIVITY VALUES (16,7,'Fix bugs as they appear','2017-03-09',28,17,0,NULL,NULL,NULL,NULL);

INSERT INTO ACTIVITY VALUES (17,7,'Identify Errors','2017-02-02',7,15,0,1,'2017-02-09','0000-00-00',0.5);

INSERT INTO ACTIVITY VALUES (18,7,'Fix Errors','2017-02-09',21,15,0,2,NULL,NULL,NULL);

INSERT INTO ACTIVITY VALUES (28,9,'Create Completed Project','2017-01-24',63,27,0,NULL,'2017-01-24','0000-00-00',0.2);

INSERT INTO ACTIVITY VALUES (29,9,'Template Dashboard Ready','2017-02-09',1,27,0,1,NULL,NULL,NULL);

/* RESOURCE ROWS 			*/

INSERT INTO RESOURCE VALUES (3,4,'Programming','Hour',100);

INSERT INTO RESOURCE VALUES (4,4,'Consulting','Hour',200);

INSERT INTO RESOURCE VALUES (10,9,'Programming','Hour',15);

INSERT INTO RESOURCE VALUES (12,7,'Development','Hour',15);

/* ACTIVITY RESROUCE ROWS   */

INSERT INTO ACTIVITY_RESOURCE VALUES (9,8,3,NULL,40);

INSERT INTO ACTIVITY_RESOURCE VALUES (10,9,3,NULL,40);

INSERT INTO ACTIVITY_RESOURCE VALUES (8,7,4,NULL,40);

INSERT INTO ACTIVITY_RESOURCE VALUES (11,9,4,NULL,40);

INSERT INTO ACTIVITY_RESOURCE VALUES (25,28,10,NULL,86);

INSERT INTO ACTIVITY_RESOURCE VALUES (26,14,12,NULL,5);

INSERT INTO ACTIVITY_RESOURCE VALUES (27,17,12,NULL,5);

INSERT INTO ACTIVITY_RESOURCE VALUES (28,18,12,NULL,15);

INSERT INTO ACTIVITY_RESOURCE VALUES (29,15,12,NULL,5);

INSERT INTO ACTIVITY_RESOURCE VALUES (30,16,12,NULL,20);

/* RESROUCE_CONSUME ROWS    */

INSERT INTO RESOURCE_CONSUME VALUES  (13,9,9,'2017-01-05');

INSERT INTO RESOURCE_CONSUME VALUES  (12,8,1,'2017-01-08');

INSERT INTO RESOURCE_CONSUME VALUES  (15,8,9,'2017-01-09');

INSERT INTO RESOURCE_CONSUME VALUES  (14,11,1,'2017-01-09');

INSERT INTO RESOURCE_CONSUME VALUES  (19,25,16,'2017-02-02');

INSERT INTO RESOURCE_CONSUME VALUES  (20,25,0.5,'2017-02-02');

INSERT INTO RESOURCE_CONSUME VALUES  (35,25,3,'2017-02-09');

INSERT INTO RESOURCE_CONSUME VALUES  (36,25,3,'2017-02-09');

INSERT INTO RESOURCE_CONSUME VALUES  (21,26,1,'2017-01-26');

INSERT INTO RESOURCE_CONSUME VALUES  (22,26,1,'2017-01-26');

INSERT INTO RESOURCE_CONSUME VALUES  (37,28,0.5,'2017-02-16');

/* QUERY AS REQUESTED	*/

SELECT PROJECT_NAME, ACTIVITY_NAME, SUM(COST_PER_UNIT * PLAN_QUANTITY) AS 'ESTIMATED COST', START_DATE AS 'PLANNED START DATE', START_DATE + INTERVAL PLAN_DURATION DAY AS 'PLANNED FINISH DATE'

FROM PROJECT, ACTIVITY, RESOURCE, ACTIVITY_RESOURCE

WHERE PROJECT.PROJECT_ID = ACTIVITY.PROJECT_ID

AND ACTIVITY.ACTIVITY_ID = ACTIVITY_RESOURCE.ACTIVITY_ID

AND RESOURCE.RESOURCE_ID = ACTIVITY_RESOURCE.RESOURCE_ID

GROUP BY ACTIVITY.ACTIVITY_ID;